## EN
S.N.T.G.N. "TRANSGAZ" S.A. MEDIAŞ
SCHEDULE OF THE PLANNED WORKS FOR 2015 CAUSING THE REDUCTION OR INTERRUPTIONS OF THE FIRM TRANSMISSION CAPACITY IN THE DEDICATED TRANSMISSION PIPELINE (DTP)
Item no. | Name of the work | Intervention area | Affected Exit/Entry point | [7 empty] | AFFECTED RELEVANT POINT | Planned period for work execution | Date/hour interruption/reduction | Date/hour of the return to operation | Observations | Regional Office
|  |  | Exit points from the DTP |  |  |  | Entry points in the DTP
|  |  | Capacity interruption |  | Capacity reduction |  | Capacity interruption |  | Capacity reduction
|  |  | Code | Name | Code | Name | Code | Name | Code | Name | Code
I. PIPELINES REPAIRS
- | - | - | - | - |  | - |  | - |  | - | - | - | - | - | - | -
II. PIPELINES REHABILITATION
- | - | - | - | - |  | - |  | - |  | - | - | - | - | - | - | -
III. PIPELINES INSPECTIONS AND CLEANING
1 | 40" Isaccea - Negru Vodă T I | 182 km |  |  | SM1278D0 | Negru Vodă I |  |  |  |  | SM1278D0 | June - September 2015 |  |  | Capacity reduction during the PIG transition / interruption in case of PIG blocking | Constanța
IV. UPGRADING AND DEVELOPMENT OF THE DTP
- | - | - | - | - | - | - |  |  |  |  | - | - | - | - | - | -
V. MAINTENANCE DTP OBJECTIVES
1 | Replacing valves I, I1, I2 and I3 Import, to interconnection T I and Import | GMS ISACCEA |  |  |  |  | PM0278 | Isaccea I |  |  | PM0278 | July - September 2015 |  |  |  | Constanța
VI. OWN SOURCES MAINTENANCE OF THE DTP OBJECTIVES
- | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
VII. WORKS REQUESTED BY THIRD PARTIES (undercrossings, deviations, etc.)
- | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -